## Tasks
Term 2
TO DO
Task ID | Task Name | Assignee | Due Date | Priority
86a6c7xp0 | Release 1 |  | 2025-02-23
86a6c86ka | Ask AWG for the retail location data | Flavien Foreste
86a6c86p2 | Gather data related to the retail location and process them to find the key retailers | Matteo Scarpa, Shan Chung, Jimmy Chen, Jingyi Liu, Flavien Foreste
86a6c7xrt | Release 2 |  | 2025-03-16
86a6c88gm | Identify trends and factors influencing engagement from retailer and participant data | Jingyi Liu, Shan Chung, Flavien Foreste, Jimmy Chen, Matteo Scarpa
86a6c88x0 | Develop and present targeted potential strategies for improving engagement | Shan Chung, Flavien Foreste, Jingyi Liu, Jimmy Chen, Matteo Scarpa
86a6c7xt3 | Release 3 |  | 2025-04-13
86a6c89hf | Understand what are the key KPIs related to the program
86a6c89yg | Design and build an interactive dashboard for KPI tracking
86a6c8a2n | Develop a machine learning model to predict next year’s non profit- participation
86a6c8a5r | Validate the model
86a6c7xty | Release 4 |  | 2025-05-11
86a6c8j30 | Select the best machine-learning methods to execute the budget report
86a6c8j66 | Structure the budget report and highlight the key findings from analysis
86a6c7xwj | Final Deliverable